## Lifecycle Phases Overview
Phase Timing Boundaries (derived from above)
Phase | Approximate Time Window | Notes
1. Ideation | 12+ months → 3 months before | Start point driven entirely by event format chosen; no fixed deadline
2. Initial Request | 9+ months → 12 weeks before | Space Request Form is the hard anchor at 12+ weeks; external venues require 9 months
3. Coordinated Planning | 6 months → 2 weeks before | Runs concurrently with Phase 4; densest deadline cluster sits at the 4-week mark
4. Content Planning | 6 weeks → 2 weeks before | Runs concurrently with Phase 3; Promo Group review is the closing milestone at 2–4 weeks
5. Pre-Event Execution | 2 weeks → day before | Hard window; no major changes permitted within 48 hours of event
6. Event Day | T − 90 min → event close | Fixed sequence from team arrival through doors open
7. Post-Event Closure | Day after → 1 month after | Budget reconciliation at 10 working days and reporting form at 1 month are the hard closing anchors
>> our tool in its ultimate version will cover the first 5 phases. It will help guide students and help Jo project manage all events
It will inform the students
MVP will cover the 1st 3 phases
Tool can pre-populate submission forms and help with the next steps

## Timelines within Phase
Event Lifecycle: All Timelines Mapped to Phases
Note on phase timing: Phases 1 and 2 have variable start points determined by event type and complexity — the format choice in Phase 1 sets the minimum lead time for everything downstream. Phases 3 and 4 run concurrently, not sequentially. Phase 5 is the fixed final 2-week window. All deadline anchors below are measured from the event date.
Time Relative to Event | Component | Phase
VARIABLE — set by event format choice
12+ months before | Conference / Summit: begin ideation | 1
12+ months before | Strategic Event identification with Editorial Planning | 1
6+ months before | Hybrid event: begin ideation | 1
3–4 months before | Workshop / Panel / Networking / Fireside: begin ideation | 1
FIXED PLANNING HORIZON
9 months before | External venue: submit booking and begin procurement assessment | 2
6–12 months before | Tier 1 (dream) speaker outreach begins | 3
6 months before | Dean attendance request — ideal lead time | 3
3–6 months before | Tier 2 speaker outreach begins | 3
3–6 months before | Sponsorship conversations begin — note: many companies set annual budgets April–August for following year; financial year-end budgets available December / March | 3
3 months before | Complex AV / live streaming: contact | 3
avhelp@london.edu
3 months before | Dean attendance request — minimum notice for student organisers | 3
3 months before | Tier 1 speaker: target confirmation deadline for use in event promotion | 3
12+ weeks before | Space Request Form submitted to | 2
space@london.edu
2 months before | Nuffield Hall AV: contact | 3
avhelp@london.edu
COORDINATED PLANNING WINDOW
6 weeks before | Speaker initial briefing document sent | 3
6 weeks before | Media / PR planning: engage | 4
editorialplanning@london.edu
— hard minimum
4–6 weeks before | Event Promotion Form submitted for central promotional support | 4
4 weeks before | EIS submitted to Duty Manager team — Key Events only | 3
4 weeks before | Speaker list submitted to Security at | 3
speakersandguests@london.edu
4 weeks before | BSL interpreters booked | 3
4 weeks before | AV requirements confirmed — standard events | 3
~4 weeks before | Key Events Meeting invitation received from Duty Manager team | 3
4 weeks before | Speaker briefing call scheduled | 3
30 days before | Catering order submitted to | 3
cateringevents@london.edu
2–4 weeks before | Event Promo Group review takes place | 4
3 weeks before | Key Events Meeting attended — mandatory for Key Events (Thursdays 11am, Teams) | 3
3 weeks before | Welcome desk booked | 3
2 weeks before | Finance code approved and confirmed in place | 3
PRE-EVENT EXECUTION WINDOW
2 weeks before | Final programme shared with all speakers | 5
1–2 weeks before | Written team brief distributed to all staff and volunteers | 5
1 week before | Final speaker arrangements confirmed | 5
1 week before | BSL materials provided to interpreters | 5
7 days before | Final catering numbers confirmed | 5
7 days before | Alcohol order placed — minimum deadline | 5
7 days before | Final speaker changes or additions submitted to Security | 5
7 days before | All Campus Services teams: final requirements received | 5
5 days before | Dietary requirements list sent to catering — names removed per GDPR | 5
48–72 hours before | Final guest list submitted to Security; registration closed to new attendees | 5
48–72 hours before | Final headcount sent to all suppliers | 5
72 hours before | Final catering / alcohol adjustments — emergencies only | 5
48 hours before | 48-hour attendee reminder email sent | 5
48 hours before | 48-hour rule: no major event changes unless absolutely critical | 5
Day before | Technical rehearsal — complex events | 5
Day before | Venue walk-through with Duty Manager | 5
Day before | Verbal team briefing conducted | 5
Day before | All technology tested; Teams / WhatsApp comms groups confirmed live | 5
Day before | Weather contingency decision made and communicated | 5
EVENT DAY
T − 90 min | Full team arrives on site | 6
T − 60 min | Supplier setup begins; final AV check for standard events | 6
T − 45 min | Final team briefing huddle | 6
T − 30 min | Registration desk live | 6
T − 15 min | Welcome team in position | 6
T + 0 | Doors open | 6
POST-EVENT CLOSURE
Within 24 hours | Thank speakers, VIPs, and major sponsors; post social media highlights | 7
Within 48 hours | Thank all attendees, volunteers, staff, and Campus Services teams | 7
Within 1 week | Structured team debrief; begin invoice collection; start budget reconciliation | 7
Within 2 weeks | Expense claims completed; recordings and follow-up resources distributed to attendees | 7
Within 10 working days | Budget reconciliation completed — target deadline | 7
Within 1 month | Final budget report produced; all payments processed; LBS event reporting form submitted | 7

## Stakeholders by Phase
Phase | Stakeholder | Timeline | Workstream / Task
1. Ideation | Event Organiser | 12+ months before (Conference/Summit); 6+ months (Hybrid); 3–4 months (Workshop/Panel/Networking/Fireside) | Event necessity qualification; ROI and returns assessment; SMART objectives and KPI framework; audience definition; format selection
1. Ideation | Club ExCo | Same as Event Organiser | Validate event concept; confirm club strategic fit and resource availability
1. Ideation | Editorial Planning Team | As needed — Monday drop-ins (Teams, 2–3pm) or | Optional: validate whether event is right format; explore alternative channels; general strategic guidance
editorialplanning@london.edu
2. Initial Request | Event Organiser | Immediately after ideation | Submit Space Request Form; initiate all Phase 2 submissions; appoint Deputy Event Organiser
2. Initial Request | Club ExCo / Deputy Event Organiser | Immediately after ideation | Team structure confirmed; functional roles assigned (Content, Marketing, Budget, Operations); role clarity test applied
2. Initial Request | Space Management | 12+ weeks before (Key Event scale); 4–12 weeks (standard); <4 weeks (low-risk small student gatherings with written explanation of urgency) | Receive Space Request Form; determine Key Event status; confirm venue and Event ID; notify if EIS required
2. Initial Request | Events Oversight Group | Before scheduled review date — earlier submission allows additional review cycles | Business case review; approval, rejection, or conditional approval with stated requirements
2. Initial Request | Editorial Planning Team | 3+ months before event if Dean involvement needed | Route Dean invitation request; advise on event positioning and institutional fit
2. Initial Request | SA Treasury | As soon as event concept is confirmed | Finance code approval; SA platform access (Campus Groups / Eventscase); SA Club Support Fund application if applicable
2. Initial Request | SA Sponsorship | When sponsorship strategy is defined | Confirm sponsorship framework and package structure; route all agreements — clubs cannot sign contracts directly
2. Initial Request | Advancement Team | Before any alumni or donor outreach | Notify of event concept; flag any managed relationships to avoid duplication
2. Initial Request | DPO | If under-18 attendance is identified | Provide Child Contributor Consent Form; advise on GDPR obligations specific to the event
3. Coordinated Planning | Tier 1 Speakers | 6–12 months before | Outreach and invitation; target confirmation by 3 months before for promotional use
3. Coordinated Planning | Tier 2 Speakers | 3–6 months before | Outreach and invitation
3. Coordinated Planning | Tier 3 / Backup Speakers | As needed | Available at shorter notice; confirm quickly to fill gaps
3. Coordinated Planning | Faculty | 3–4 months before | Invitation with programme context; flexible around teaching schedule
3. Coordinated Planning | Dean's Office | 3–6 months before — via | Dean invitation routing; crib sheet (
|  | editorialplanning@london.edu | text_mksdvrxy
|  | only; never contact directly | ) prepared and linked once attendance confirmed
3. Coordinated Planning | Advancement Team | Before any direct alumni or donor contact | Speaker list shared for donor intelligence; alumni speaker invitations routed through Advancement if needed
3. Coordinated Planning | All Confirmed Speakers | 6 weeks before | Initial briefing document sent
3. Coordinated Planning | All Confirmed Speakers | 4 weeks before | Briefing call conducted; consent form secured before recording or streaming is publicly promoted
3. Coordinated Planning | All Confirmed Speakers | 3–6 months before if international | Travel and accommodation arranged; visa support letters if needed
3. Coordinated Planning | AV Team | 3 months before — complex events / live streaming | Contact
avhelp@london.edu
; specify multi-camera, streaming, and network port requirements
3. Coordinated Planning | AV Team | 2 months before — Nuffield Hall events | Contact
avhelp@london.edu
; agree full technical setup
3. Coordinated Planning | AV Team | 4 weeks before — standard events | Confirm AV requirements
3. Coordinated Planning | Catering Team | 4–6 weeks before | Initial menu discussion and brief with
cateringevents@london.edu
3. Coordinated Planning | Catering Team | 30 days before | Catering order submitted; must be confirmed in writing — event will not proceed without written confirmation
3. Coordinated Planning | Security Team | 4 weeks before | Speaker list submitted to
speakersandguests@london.edu
; sensitive or high-profile speakers flagged
3. Coordinated Planning | Security Team | 1 week before | Final speaker changes or additions submitted
3. Coordinated Planning | Duty Managers | 4 weeks before — Key Events | EIS submitted via submission form
3. Coordinated Planning | Duty Managers | ~4 weeks before — Key Events | Key Events Meeting invitation received; if not received contact
dutymanagers@london.edu
3. Coordinated Planning | Duty Managers | 3 weeks before — Key Events | Key Events Meeting attended — mandatory; missing may result in event cancellation
3. Coordinated Planning | Estates / Porters | 4+ weeks before | Room layout confirmed; furniture and equipment setup coordinated via
estates@london.edu
3. Coordinated Planning | Welcome Desk | 3 weeks before | Welcome desk booked via
welcomedesk@london.edu
3. Coordinated Planning | BSL Interpreters | 4 weeks before | Book interpreters via SA (
sa@london.edu
); two required for events over 1 hour
3. Coordinated Planning | All Services Teams + Organizers (student club) | 1-4 weeks before | All parties meeting to discuss the key events to happen on campus in the following month (once a week)
3. Coordinated Planning | SA Treasury | 2 weeks before | Finance code confirmed in place — required to transact
3. Coordinated Planning | SA Sponsorship | When sponsors confirmed | Sponsorship agreement executed through SA; VAT treatment clarified
4. Content Planning | Editorial Planning Team | 6 weeks before | Engage for media and PR planning — hard minimum lead time; submit via
editorialplanning@london.edu
4. Content Planning | Editorial Planning Team | 4–6 weeks before | Event Promotion Form review; editorial priority assigned (Gold / Silver / Bronze / EP Highlighted); area and editorial theme confirmed
4. Content Planning | CC Network | ~4–6 weeks before | Cross-departmental content review; collaboration opportunities identified
4. Content Planning | Editorial Group | 4–6 weeks before | Content format and angle agreed; writer assigned; content subitems created (Drafted → With writer → Briefed to web → Done)
4. Content Planning | PR / Communications Team | 6 weeks before — minimum | Media strategy developed; press outreach planned; speakers briefed on media handling
4. Content Planning | Event Promo Group | 2–4 weeks before | Promotional channel mix confirmed; messaging and creative approach agreed
4. Content Planning | Social Media Team | 2–4 weeks before | Content calendar confirmed; pre-event posts scheduled; live coverage approach agreed
4. Content Planning | Photography Team | 4 weeks before | Photographer booking confirmed; shot brief agreed; consent and privacy arrangements confirmed
4. Content Planning | Club / Personal Networks | 4–6 weeks before | Self-promotion activated: personal LinkedIn, club mailing lists, WhatsApp groups, Campus Groups listing
4. Content Planning | Confirmed Sponsors | When marketing materials go live | Sponsor recognition confirmed and applied across all promotional channels and materials
5. Pre-Event Execution | All Confirmed Speakers | 2 weeks before | Final programme shared
5. Pre-Event Execution | All Confirmed Speakers | 1 week before | Final arrangements confirmed
5. Pre-Event Execution | All Confirmed Speakers | Day before | Final check-in; arrival times and green room arrangements confirmed
5. Pre-Event Execution | Dean's Office | 2 weeks before | Confirm briefing sent and Dean fully prepared —
dean_attending__1
= Yes - briefing sent
5. Pre-Event Execution | Security Team | 7 days before | Final speaker changes or additions submitted
5. Pre-Event Execution | Security Team | 48–72 hours before | Final guest list submitted to
5. Pre-Event Execution | Security Team | 7 days before (depending on when we secure the guest's availability) | To decide whether additional security services needed depending on the identities of guests
speakersandguests@london.edu
; registration closed to new attendees immediately after
5. Pre-Event Execution | Catering Team | 7 days before | Final catering numbers confirmed; alcohol order placed — minimum deadline
5. Pre-Event Execution | Catering Team | 5 days before | Dietary requirements list submitted to
cateringevents@london.edu
— names removed per GDPR
5. Pre-Event Execution | Catering Team | 72 hours before | Final adjustments — emergencies only
5. Pre-Event Execution | All Campus Services Teams | 7 days before | Final requirements confirmed across all teams
5. Pre-Event Execution | All Suppliers | 48–72 hours before | Final headcount confirmed
5. Pre-Event Execution | AV Team | Day before — complex events | Full technical rehearsal
5. Pre-Event Execution | AV Team | T–60 min — standard events | Final AV check
5. Pre-Event Execution | Duty Managers | Day before | Venue walk-through
5. Pre-Event Execution | BSL Interpreters | 1 week before | Final event materials provided
5. Pre-Event Execution | Welcome Desk | Day before | Final briefing
5. Pre-Event Execution | Team / Volunteers | 1–2 weeks before | Written brief distributed
5. Pre-Event Execution | Team / Volunteers | Day before | Verbal briefing conducted; Teams / WhatsApp comms groups confirmed live and tested
5. Pre-Event Execution | Attendees | 48 hours before | 48-hour reminder email sent: timing, location, transport, dress code, dietary confirmation, WiFi, contact number
6. Event Day | Duty Managers | From T–90 min | Central on-site coordination and emergency response — Sussex Place: 07966 907 265; Sammy Ofer: 07976 806 120
6. Event Day | Security Team | From T–90 min | On-site security; VIP arrival management; capacity and access control — Control room: 02070 006 888
6. Event Day | AV Team | From T–90 min | On-site technical support throughout event
6. Event Day | Catering Team | Per event schedule | Food and beverage service delivery — Catering Duty Manager on call: 07966 907 871
6. Event Day | Estates / Porters | T–90 min | Final room setup; signage placement; on-call for adjustments — out of hours: 07966 907 890
6. Event Day | Welcome Desk | T–30 min | Registration support; guest wayfinding; health and safety attendance tracking
6. Event Day | Photography Team | Throughout event | Content capture per agreed shot brief; respect opt-out indicators (red dots / wristbands)
6. Event Day | Social Media Team | Throughout event | Live coverage; real-time posts using
#WhyILoveLBS
6. Event Day | Speakers / VIPs | Per run of show | Programme delivery; green room managed throughout by dedicated team member
6. Event Day | Team / Volunteers | From T–90 min | Deployed across registration, ushering, Q&A, catering flow, and contingency roles; rotated every 2 hours
7. Post-Event Closure | Speakers | Within 24 hours | Personal thank you email or handwritten note
7. Post-Event Closure | VIPs / Major Sponsors / Donors | Within 24 hours | Personal thank you
7. Post-Event Closure | All Attendees | Within 48 hours | Thank you email; post-event survey if planned (max 7 questions; only if data will be acted on)
7. Post-Event Closure | Volunteers / Staff / Campus Services | Within 48 hours | Thank you communications; copy line managers for exceptional contributions
7. Post-Event Closure | Social Media Team | Within 48 hours | Follow-up posts; photo highlights published with
#WhyILoveLBS
7. Post-Event Closure | Photography Team | Within 1–2 weeks | Edited photos and videos delivered; stored securely; used only for stated purposes
7. Post-Event Closure | Editorial / Content Team | Within 2 weeks | Post-event content published (article, video, blog post); content link added to board subitem
7. Post-Event Closure | SA Treasury | Within 2 weeks | Expense claims submitted via Infor XM with itemised receipts
7. Post-Event Closure | SA Treasury | Within 1 month | Budget reconciliation completed; final budget report produced
7. Post-Event Closure | Editorial Planning Team | Within 1 month | LBS Event Reporting Form completed and submitted
7. Post-Event Closure | Club ExCo / Successor | Before end of term | Handover package: stakeholder map, supplier evaluations, speaker database, sponsor history, marketing performance, lessons learned
7. Post-Event Closure | Student Club / Editorial | Within 1–2 weeks | Make LinkedIn posts; also encourages the speakers to post/repo

## Forms by Phase
Phase | Total Forms | Mandatory (all events) | Conditional
1. Ideation | 0 | — | —
2. Initial Request | 4 | Space Request Form | Business Case (if significant scale/resources) EIS begin (if Key Event indicators present) SA Club Support Fund (if balance under £5K)
3. Coordinated Planning | 6 | Speaker Security Review Form EIS final submission (Key Events) | Risk Assessment (large/external events) Cloakroom Booking Speaker Consent (if recording) Child Contributor Consent (if under-18 approved) Sponsorship Agreement (if sponsors)
4. Content Planning | 1 | — | Event Promotion Form (if seeking central support)
5. Pre-Event Execution | 2 | Final Guest List Form | Media Release Form (intimate events only)
6. Event Day | 0 | — | —
7. Post-Event Closure | 2 | LBS Event Reporting Form | Expense Claim Form (if reimbursements needed)

## Database Sources
Phase | Stakeholder | Data | Have?
3 | SA Finance | Finance Code Directory | FALSE
|  | Student Toolkit | FALSE
|  | Space Request Form_Completed | FALSE
|  | EIS_Completed | FALSE
|  | Business Case_Completed | FALSE
|  | SA Club Support Fund_Request | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE